## Sheet1
Item | Risk | control | Response | Impact | Likelyhood | Risk level | [5 empty] | likelyhood
Hardware Issues | My computer could fail, break or be damaged by external factors | Minimum movment of the machine and no harmful liquids place over the computer | Inform a QA traineer strait away and ask for hoe to proceed | 5 | 2 | 10 |  |  | low | medium low | medium | medium high | high
Software issues | Software updates could break files and or the computer itself | Ensure backups and reasonable care when updating the software | Ask a QA traineer and or internet forum for help reovling the issuse | 4 | 1 | 4 |  | critical | 5 | 10 | 15 | 20 | 25
Illness | During the project I could become sick and or injured | I should try to avoid enviroments where this is likley | Infor QA of your need to be absent and Ask for more time to complete the project | 3 | 2 | 6 |  | serious | 4 | 8 | 12 | 16 | 20
Bad internet connection | Could stop me from uploading the project or atending learning of the presentation | ensure good quality of internet and avoid changing providers during this time | Do what you can do while the internet is down, contact your IPS to fix the issue, use mobile data as a last resort | 3 | 2 | 6 | Impact | moderate | 3 | 6 | 8 | 12 | 15
Unable to complete Task | Due to lack of applyable knlowege or understanding I could fail to impliment the project to sufficant standard | Ensure that I use all resoucrse avalible e.g. QA community/ QA instructors to resolve issues I might have | Ask for help or explain why the task could be done in the presentaion | 4 | 2 | 8 |  | minor | 2 | 4 | 6 | 8 | 10
Malicious people/software | During the building of the project I could be hacked or install malicious software e.g. ransomware | Ensure antivirus is upto date and avoid downloading from or clicking on qustionable links | Reset your comupter and obtain needed files from backup | 5 | 1 | 5 |  | negligable | 1 | 2 | 3 | 4 | 5
Broken version pushed to the main | Pushing to the main and overwirte it with broken or no code will remove the project and backup | ensure that dev is only pushed to and avoid the main at all cost | Revert the main and push the correct code | 3 | 2 | 6
Insufficiant Testing | Through incorrectly testing and or missing important tests the delivered version could contain bugs | Ensure good test coverage and for UI have a fail test condition too | Try to get most coverage psooible and ask for help | 3 | 3 | 9
Incorrect or insuficiant documentaion | During the making of the README file I could give incorrect or insuficiant information on how to setup the project. | throughtly test the README info and give to others to use and test | Get all the documtenation done as soon as can be done to ensure it is upto date | 3 | 2 | 6
Unexplianable errors | During the creation of the code or complie errors could come up which cannt be easily fixed with my knowlegde | Ensure plenty of time at the end of the project to give time to fix errors or find work arrounds | Ask for QA traineer help or Explain and theories the solution for the problem in the presentaion | 5 | 3 | 15
Communication problems | Druing the creation of the code there could be issues with how the front and backend talk to one another | Ensure that the correct values and sytax are used on both JAVA and JavaScript to avoid this issue | Try to find the cause through testing and compare the passing tests to how JavaScript is written | 4 | 2 | 8